## excel (27)
/No Proyecto/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 25.6 | 44.9 | 29.3
Planned Time | 0.18472 |  | 0.64028
Actual Tiempo |  | 0.10764 | 0.60694
CPI (Cost-Performance Index) |  |  | 1.05
% Reuse | 0% | 0% | 0%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 6.43 | 0 | 4.68
Total Defects/KLOC or equivalent | 51.4 | 17.2 | 42.2
Yield % | 81.2% | 100% | 83.3%
Code Review Rate | 9203 | 1392 | 3660
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:31 PM el 20/03/2017