## excel (28)
/No Proyecto/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 37 | 37 | 124
Deleted (D) | 0 | 0 | 24
Modified (M) | 3 | 19 | 36
Added (A) | 111 | 97 | 391
Reused (R) | 0 | 0 | 0
Added and Modified (A+M) | 114 | 116 | 427
Total Size (T) | 148 | 134 | 491
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 110 | 116 | 340
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 12:32 PM el 20/03/2017